## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a researcher/product team member, I want to generate realistic and diverse synthetic personas from product, target audience and research inputs so that I can simulate customer behaviour. | Must Have | Ollama/local AI model; MongoDB | T.Preethika | Completed
Sprint 2 | Sprint 2 | US-02 | As a researcher, I want to ask one survey question to all synthetic personas and view relevant individual responses so that I can identify common and contrasting customer opinions. | Must Have | US-01; generated personas | T.Preethika | Completed
Sprint 3 | Sprint 3 | US-03 | As a researcher, I want to conduct a multi-turn interview with a selected persona, generate research insights and a product recommendation score, visualize experiment results and validation insights, and prepare research documentation so that I can understand customer needs, evaluate product potential, and present the completed project. | Must Have | US-01; generated personas; interview persona data; survey/interview results | T.Preethika | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-01 | T1 | Define persona generation inputs and required persona fields | 2026-07-27 | 2026-07-27 | T.Preethika | Analysis | Completed | 2 | Day 1: 2
US-01 | T2 | Design and refine synthetic persona generation prompt | 2026-07-28 | 2026-07-30 | T.Preethika | Development | Completed | 4 | Day 1: 4
US-01 | T3 | Integrate Ollama local model with Flask backend | 2026-07-30 | 2026-08-01 | T.Preethika | Development | Completed | 4 | Day 1: 4
US-01 | T4 | Store generated personas in MongoDB | 2026-08-01 | 2026-08-03 | T.Preethika | Development | Completed | 3 | Day 2: 3
US-01 | T5 | Connect Synthetic Users React page to backend and display personas | 2026-08-03 | 2026-08-05 | T.Preethika | Development | Completed | 4 | Day 3: 4
US-01 | T6 | Test persona generation and fix JSON/ObjectId response issues | 2026-08-05 | 2026-08-06 | T.Preethika | Testing | Completed | 3 | Day 5: 3
US-02 | T7 | Implement survey question submission to all personas | 2026-08-13 | 2026-08-15 | T.Preethika | Development | Completed | 4 | Day 1: 4
US-02 | T8 | Generate persona-grounded survey responses | 2026-08-14 | 2026-08-18 | T.Preethika | AI Integration | Completed | 5 | Day 1: 5
US-02 | T9 | Align survey API response structure with React UI | 2026-08-18 | 2026-08-20 | T.Preethika | Development | Completed | 3 | Day 2: 3
US-02 | T10 | Generate survey research insights from persona responses | 2026-08-20 | 2026-08-23 | T.Preethika | AI Integration | Completed | 4 | Day 3: 4
US-02 | T11 | Generate survey product recommendation score out of 100 | 2026-08-24 | 2026-08-26 | T.Preethika | AI Integration | Completed | 3 | Day 4: 3
US-02 | T12 | Test survey responses, insights and recommendation display | 2026-08-27 | 2026-08-28 | T.Preethika | Testing | Completed | 3 | Day 5: 3
US-03 | T13 | Implement persona selection for Interview Mode | 2026-09-14 | 2026-09-14 | T.Preethika | Development | Completed | 2 | Day 1: 2
US-03 | T14 | Implement multi-turn interview conversation history | 2026-09-14 | 2026-09-15 | T.Preethika | Development | Completed | 4 | Day 1: 4
US-03 | T15 | Create persona-consistent interview response prompt | 2026-09-15 | 2026-09-15 | T.Preethika | AI Integration | Completed | 4 | Day 1: 4
US-03 | T16 | Generate interview research insights | 2026-09-15 | 2026-09-16 | T.Preethika | AI Integration | Completed | 3 | Day 3: 3
US-03 | T17 | Generate interview product recommendation score and reason | 2026-09-16 | 2026-09-16 | T.Preethika | AI Integration | Completed | 3 | Day 4: 3
US-03 | T18 | Fix rating display and validate complete interview flow | 2026-09-16 | 2026-09-17 | T.Preethika | Testing | Completed | 3 | Day 5: 3
US-03 | T19 | Build Insights and Experiment Results Dashboard with theme clusters, sentiment breakdown, key persona quotes and product validation scores | 2026-09-15 | 2026-09-16 | T.Preethika | Development | Completed | 5 | Day 3: 5
US-03 | T20 | Develop Research Report Generation Module to compile persona profiles, response highlights, insight summary and validation scoring into a structured downloadable report | 2026-09-16 | 2026-09-17 | T.Preethika | Development | Completed | 5 | Day 4: 5
US-03 | T21 | Conduct end-to-end testing across persona generation, Survey Mode, Interview Mode, insight extraction and report generation; test with up to 100 personas and handle waiting, timeout or email-related issues | 2026-09-17 | 2026-09-17 | T.Preethika | Testing | Completed | 4 | Day 5: 4
US-03 | T22 | Prepare technical documentation, project report and final demonstration | 2026-09-17 | 2026-09-17 | T.Preethika | Documentation | Completed | 4 | Day 6: 4
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Setting up persona generation flow and deciding required persona fields. | Defined persona schema and generation requirements.
Sprint 1 | Day 5 | Local AI response formatting and MongoDB integration needed testing. | Refined prompts and tested persona persistence.
Sprint 1 | Day 7 | Minor API/data-format issues during persona display. | Fixed response handling and verified Synthetic Users page.
Sprint 2 | Day 1 | Survey response format had to match the React UI. | Aligned backend response structure with frontend expectations.
Sprint 2 | Day 4 | Some AI responses were too generic or not sufficiently persona-specific. | Strengthened persona-grounded survey prompt and tested different opinions.
Sprint 2 | Day 7 | Survey insights and score required end-to-end validation. | Tested survey responses, insights and /100 recommendation score.
Sprint 3 | Day 1 | Interview history and selected-persona context needed to remain consistent. | Implemented conversation history and persona context.
Sprint 3 | Day 4 | Interview rating needed correct numeric display in the UI. | Fixed rating state/display to show the score out of 100.
Sprint 3 | Day 4 | Final integration, experiment results dashboard, report generation, testing and documentation needed to be combined with the completed Interview Mode. | Completed end-to-end validation across persona generation, Survey Mode and Interview Mode; completed experiment results/dashboard work, report preparation and final documentation.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-27 | 2026-08-06 | T.Preethika | Start testing generated persona data early with multiple persona counts. | Stop relying on unvalidated model output without checking its JSON structure. | Continue modular Flask functions and simple React integration. | Added validation and tested persona generation, storage and display.
2 | Sprint 2 | 2026-08-13 | 2026-08-28 | T.Preethika | Start testing survey responses from different persona types and viewpoints. | Stop using generic prompts that can produce repetitive or irrelevant answers. | Continue keeping backend response structures consistent with frontend expectations. | Refined survey prompts and fixed persona/response API mapping.
3 | Sprint 3 | 2026-09-14 | 2026-09-17 | T.Preethika | Start validating the complete interview and reporting flow after every major UI/backend change. | Stop treating UI display, API contract and end-to-end testing issues as separate problems. | Continue maintaining conversation history, persona consistency, modular backend functions and testing. | Completed Interview Mode, research insights and product recommendation score; combined final integration work for experiment results/dashboard, research report preparation, end-to-end testing and technical documentation.
4
5
6
7